MSc_AirQuality_Timeline_Enhanced (1)

[Company]

# MSc Final Project: Predictive Air Quality Modelling

1. Project Setup

Kernel Submitted (Start: 2025-03-15, End: 2025-03-17, 3d)

Supervisor Assigned (Start: 2025-04-05, End: 2025-04-07, 3d)

Proposal Writing (Start: 2025-04-07, End: 2025-05-31, 55d)

Topic

Proposal Approval (Start: 2025-06-01, End: 2025-06-07, 7d)

2. Data Preparation

API Access (Start: 2025-06-08, End: 2025-06-12, 5d)

Merging & Cleaning (Start: 2025-06-13, End: 2025-06-23, 11d)

Feature Engineering (Start: 2025-06-24, End: 2025-07-04, 11d)

EDA Outputs (Start: 2025-07-05, End: 2025-07-12, 8d)

3. Modelling

RF, SVM, Ridge (Start: 2025-07-13, End: 2025-07-24, 12d)

Evaluation Metrics (Start: 2025-07-25, End: 2025-07-31, 7d)

Supervisor Checkpoint (Start: 2025-08-01, End: 2025-08-03, 3d)

4. AI Models (Optional)

MLP, LSTM, Transformer (Start: 2025-08-04, End: 2025-08-14, 11d)

Comparative Evaluation (Start: 2025-08-15, End: 2025-08-24, 10d)

5. Visualisation

Time-Series & Maps (Start: 2025-09-01, End: 2025-09-10, 10d)

Wind/Satellite Visuals (Start: 2025-09-11, End: 2025-09-17, 7d)

Prediction vs Sensor (Start: 2025-09-18, End: 2025-09-21, 4d)

6. Report Drafting

Intro, Methods, Results (Start: 2025-10-01, End: 2025-10-21, 21d)

Ethics, Visuals, Appendices (Start: 2025-10-22, End: 2025-10-28, 7d)

Feedback and Revisions (Start: 2025-11-01, End: 2025-11-07, 7d)

Final Referencing (Start: 2025-11-08, End: 2025-11-09, 2d)

7. Submission

Proofreading & Formatting (Start: 2025-12-01, End: 2025-12-10, 10d)

Backup and Turnitin Upload (Start: 2026-01-01, End: 2026-01-02, 2d)

Topic

| Start Date | 27 Mar 2025 |
| --- | --- |
| End Date | 12 Dec 2025 |
| Duration | 187 days? |

# 1. Project Setup

| Start Date | 27 Mar 2025 |
| --- | --- |
| End Date | 13 Aug 2025 |
| Duration | 57 days |

## Kernel Submitted (Start: 2025-03-15, End: 2025-03-17, 3d)

| Start Date | 27 Mar 2025 |
| --- | --- |
| End Date | 31 Mar 2025 |
| Duration | 3 days |

## Supervisor Assigned (Start: 2025-04-05, End: 2025-04-07, 3d)

| Start Date | 14 Apr 2025 |
| --- | --- |
| End Date | 16 Apr 2025 |
| Duration | 3 days |

## Proposal Writing (Start: 2025-04-07, End: 2025-05-31, 55d)

| Start Date | 09 Jun 2025 |
| --- | --- |
| End Date | 13 Aug 2025 |
| Duration | 48 days |

## Topic

| Start Date | 09 Jun 2025 |
| --- | --- |
| End Date | 09 Jun 2025 |
| Duration | 0 days |

## Proposal Approval (Start: 2025-06-01, End: 2025-06-07, 7d)

| Start Date | 11 Jun 2025 |
| --- | --- |
| End Date | 13 Jun 2025 |
| Duration | 3 days |

# 2. Data Preparation

| Start Date | 09 Jun 2025 |
| --- | --- |
| End Date | 16 Jul 2025 |
| Duration | 28 days |

## API Access (Start: 2025-06-08, End: 2025-06-12, 5d)

| Start Date | 09 Jun 2025 |
| --- | --- |
| End Date | 13 Jun 2025 |
| Duration | 5 days |

## Merging & Cleaning (Start: 2025-06-13, End: 2025-06-23, 11d)

| Start Date | 13 Jun 2025 |
| --- | --- |
| End Date | 27 Jun 2025 |
| Duration | 11 days |

## Feature Engineering (Start: 2025-06-24, End: 2025-07-04, 11d)

| Start Date | 19 Jun 2025 |
| --- | --- |
| End Date | 04 Jul 2025 |
| Duration | 11 days |

## EDA Outputs (Start: 2025-07-05, End: 2025-07-12, 8d)

| Start Date | 07 Jul 2025 |
| --- | --- |
| End Date | 16 Jul 2025 |
| Duration | 8 days |

# 3. Modelling

| Start Date | 14 Jul 2025 |
| --- | --- |
| End Date | 05 Aug 2025 |
| Duration | 17 days |

## RF, SVM, Ridge (Start: 2025-07-13, End: 2025-07-24, 12d)

| Start Date | 14 Jul 2025 |
| --- | --- |
| End Date | 29 Jul 2025 |
| Duration | 12 days |

## Evaluation Metrics (Start: 2025-07-25, End: 2025-07-31, 7d)

| Start Date | 22 Jul 2025 |
| --- | --- |
| End Date | 31 Jul 2025 |
| Duration | 7 days |

## Supervisor Checkpoint (Start: 2025-08-01, End: 2025-08-03, 3d)

| Start Date | 01 Aug 2025 |
| --- | --- |
| End Date | 05 Aug 2025 |
| Duration | 3 days |

# 4. AI Models (Optional)

| Start Date | 14 Aug 2025 |
| --- | --- |
| End Date | 28 Aug 2025 |
| Duration | 11 days |

## MLP, LSTM, Transformer (Start: 2025-08-04, End: 2025-08-14, 11d)

| Start Date | 14 Aug 2025 |
| --- | --- |
| End Date | 28 Aug 2025 |
| Duration | 11 days |

## Comparative Evaluation (Start: 2025-08-15, End: 2025-08-24, 10d)

| Start Date | 15 Aug 2025 |
| --- | --- |
| End Date | 28 Aug 2025 |
| Duration | 10 days |

# 5. Visualisation

| Start Date | 01 Sep 2025 |
| --- | --- |
| End Date | 23 Sep 2025 |
| Duration | 17 days |

## Time-Series & Maps (Start: 2025-09-01, End: 2025-09-10, 10d)

| Start Date | 01 Sep 2025 |
| --- | --- |
| End Date | 12 Sep 2025 |
| Duration | 10 days |

## Wind/Satellite Visuals (Start: 2025-09-11, End: 2025-09-17, 7d)

| Start Date | 11 Sep 2025 |
| --- | --- |
| End Date | 19 Sep 2025 |
| Duration | 7 days |

## Prediction vs Sensor (Start: 2025-09-18, End: 2025-09-21, 4d)

| Start Date | 18 Sep 2025 |
| --- | --- |
| End Date | 23 Sep 2025 |
| Duration | 4 days |

# 6. Report Drafting

| Start Date | 01 Oct 2025 |
| --- | --- |
| End Date | 11 Nov 2025 |
| Duration | 30 days |

## Intro, Methods, Results (Start: 2025-10-01, End: 2025-10-21, 21d)

| Start Date | 01 Oct 2025 |
| --- | --- |
| End Date | 29 Oct 2025 |
| Duration | 21 days |

## Ethics, Visuals, Appendices (Start: 2025-10-22, End: 2025-10-28, 7d)

| Start Date | 22 Oct 2025 |
| --- | --- |
| End Date | 30 Oct 2025 |
| Duration | 7 days |

## Feedback and Revisions (Start: 2025-11-01, End: 2025-11-07, 7d)

| Start Date | 03 Nov 2025 |
| --- | --- |
| End Date | 11 Nov 2025 |
| Duration | 7 days |

## Final Referencing (Start: 2025-11-08, End: 2025-11-09, 2d)

| Start Date | 10 Nov 2025 |
| --- | --- |
| End Date | 11 Nov 2025 |
| Duration | 2 days |

# 7. Submission

| Start Date | 09 Jun 2025 |
| --- | --- |
| End Date | 12 Dec 2025 |
| Duration | 135 days |

## Proofreading & Formatting (Start: 2025-12-01, End: 2025-12-10, 10d)

| Start Date | 01 Dec 2025 |
| --- | --- |
| End Date | 12 Dec 2025 |
| Duration | 10 days |

## Backup and Turnitin Upload (Start: 2026-01-01, End: 2026-01-02, 2d)

| Start Date | 09 Jun 2025 |
| --- | --- |
| End Date | 10 Jun 2025 |
| Duration | 2 days |

# Topic

| Start Date | 09 Jun 2025 |
| --- | --- |
| End Date | 09 Jun 2025 |
| Duration | 1 day? |